## Sheet1
CLASS 3300 INTRO TO SOFTWARE ENGINEERING
TEAM: | Jack Dodge, West Manison, George Morales, Sebastian Sanchez
REQ Lead: | West Manison
LAST UPDATE: | 2025-02-26
Team Project - Requirement Spreadsheet
|  | CONFIGURATION MANAGEMENT |  |  | TEST |  |  | Outstanding Issues |  | Final DELIVERY |  | Comments
REQUIREMENT |  | Team Member | Due Date | Progress | Test Method | Team Member | Date Tested |  | # Flags Resolved
[8 empty] | # Flags |  | Ver | Date
Everyone
| Midterm Presentation (SDP) |  | 2025-03-05 | In-Progress
| SDP |  | 2025-03-05 | In-Progress
| Github Repo |  | 2025-03-12 | In-Progress
| Github Pages/DNS provider |  | 2025-03-12 | In-Progress
| Website |  | 2025-03-19 | In-Progress
| Final Presentation (SDR) |  |  | Need-To-Start
Jack Dodge
West Manison
| Color of O | Manison | 2025-03-12 | Need-To-Start | T
| Color of X | Manison | 2025-03-12 | Need-To-Start | T
| Color of Board | Manison | 2025-03-12 | Need-To-Start | T
| Background Color | Manison | 2025-03-08 | Need-To-Start | T
| Interactivity | Manison | 2025-03-26 | Need-To-Start | T, A, I, O
| Winning algorithm | Manison | 2025-04-02 | Need-To-Start | T, A, I, O
| Tic Tac Toe Game | Manison | 2025-04-30 | Need-To-Start | A, O
George Morales
Sebastian Sanchez
EXAMPLE |  | T Write | 2025-03-05 |  |  |  | 2025-03-07 | 3 | all | IT 2.3 | 2025-03-09
Late by 1-7 days
Late by more than a week
T,A, I, O
test
analysis
inspection
observation