## Sheet1
CLASS 3300 INTRO TO SOFTWARE ENGINEERING
TEAM: | Jack Dodge, West Manison, George Morales, Sebastian Sanchez
REQ Lead: | West Manison
LAST UPDATE: | 2025-04-21
Team Project - Requirement Spreadsheet
|  |  |  | TEST |  |  | Outstanding Issues |  | Final DELIVERY |  | Comments
REQUIREMENT |  | Due Date | Progress | Test Method | Team Member | Date Tested |  | # Flags Resolved
[7 empty] | # Flags |  | Ver | Date
Everyone
SDP |  | 2025-03-05 | In-Progress
| Add individual requirements | 2025-03-01 | Completed |  | Everyone
| Midterm Presentation (SDP) | 2025-03-05 | Completed |  | Everyone
Documentation
Website |  | 2025-03-19 | In-Progress |  | Everyone
| Setup Github Repo | 2025-03-12 | Completed |  | Everyone | 2025-03-28 | 0
| Github Pages/DNS provider | 2025-03-12 | Completed | T, O | Everyone | 2025-03-28 | 1 | 1
| Home page | 2025-03-24 | In-Progress |  | Everyone
| Font color | 2025-03-24 | Completed | O | Everyone | 2025-03-30 | 0
| Font | 2025-03-24 | Completed | O | Everyone | 2025-03-31 | 0
| Links color | 2025-03-24 | Completed | O | Everyone | 2025-04-01 | 0
| Headers | 2025-03-24 | Completed | O | Everyone | 2025-04-02 | 2 | 1
| Project cards | 2025-03-31 | In-Progress | T, O | Everyone | 2025-04-13 | 2 | 0 |  |  | Unsure if these images should be custom logos that we create or just screenshots of the project and then pasted onto some background
| LICENSE | 2025-04-03 | Completed | NONE
SDR |  |  |  |  | Everyone
| Tech Documentation | 2025-04-21 | Completed |  | Everyone
| Stretch goal analyis | 2025-03-31 | Completed |  | Everyone | 2025-04-09 | 0
Everyone
Everyone
| Final Presentation (SDR) |  | Need-To-Start |  | Everyone
Jack Dodge
| Create Random Deck | 2025-04-09 | Completed | T | Manison |  | 0
| Create "Hands" | 2025-04-09 | Completed | T | Manison |  | 0 |  |  |  | Currently drawing the cards in the hands as seperate items, will go back and try to make the cards their own object if possible.
| Setup Opponent | 2025-04-11 | Completed | T, A, I, O | Manison |  | 0 |  |  |  | Dealer always wins, and not in the metaphorical way.
| Design Environment | 2025-04-11 | Completed | T, I | Manison |  | 0
| Point System | 2025-04-18 | In-Progress | T, I, O | Manison |  | 1
| Extra: Difficulty Slider | 2025-04-18 | In-Progress | T, A, I, O | Manison |  | 2 |  |  |  | Only way to do this would be by adding extra rules, I don't think I want to do that
| Blackjack Game | 2025-04-18 | In-Progress | T, A, O | Manison
West Manison
| Color of O | 2025-04-09 | Completed | T | Morales | 2025-04-11 | 0
| Color of X | 2025-04-09 | Completed | T | Morales | 2025-04-11 | 0
| Color of Board | 2025-04-11 | Completed | T | Morales | 2025-04-11 | 0
| Background Color | 2025-04-11 | Completed | T | Morales | 2025-04-12 | 0
| Interactivity | 2025-04-18 | Completed | T, A, I, O | Morales |  | 3 | 3 |  |  | Game glitches causing the first player's symbol to be the only symbol that's 'playable'
| Winning algorithm | 2025-04-18 | Completed | T, A, I, O | Morales | 2025-04-18 | 0
| Tic Tac Toe Game | 2025-04-18 | Completed | T, A, O | Morales
| Embed HTML Form for User Input | 2025-04-11 | In-Progress | T,A | Dodge
George Morales
| Create Initial Board | 2025-04-09 | Completed | T, I | Sanchez | 2025-04-09 | 0
| Create Snake Character | 2025-04-09 | Completed | T, A, O | Sanchez | 2025-04-09 | 0
| Proper snake movement on board | 2025-04-11 | Completed | T, A, O | Sanchez | 2025-04-12 | 2 | 2
| Create object for snake to consume | 2025-04-11 | Completed | T, A, I, O | Sanchez | 2025-04-12 | 1 | 1
| Create snake length mechanichs | 2025-04-18 | Completed | T,A, I, O | Sanchez |  | 2
| Colors | 2025-04-18 | Completed | I, O | Sanchez |  | 0
| Score Tracker | 2025-04-18 | In-Progress | T, I, O | Sanchez |  | 0 | 0
| Snake Game | 2025-04-16 | Completed | T, A, O | Sanchez
Sebastian Sanchez
| Figma Website Concept | 2025-04-09 | Completed | I, O | Dodge | 2025-04-10 | 0 | 0
| Finalize Website Structure (HTML) | 2025-04-09 | Completed | T, A, I, O | Dodge |  | 2 | 0
| Finalize Website Visual (CSS) | 2025-04-11 | Completed | T, A, I, O | Dodge |  | 1 | 0
| Embed Hard-Coded Linear Algebra decrypter | 2025-04-18 | Completed | T,A | Dodge |  | 1 | 1
| Test and Debug | 2025-04-18 | In-Progress | T,A,I | Dodge
| Finalize Publication | 2025-04-18 | In-Progress | A,I,O | Dodge
STRETCH GOALS
|  | Late by 1-7 days |  | T,A, I, O
test
|  | Late by more than a week |  | analysis
inspection
observation